## Sheet1
task_id | title | assignee | status | priority | category | estimated_hours | actual_hours | tags | created_at | completed_at
TASK-101 | Design Pandas schema & file persistence layer | Meet | DONE | HIGH | Backend | 6 | 5.5 | pandas, schema, storage | 2026-10-10 10:00 | 2026-10-11 16:30
TASK-102 | Implement NumPy statistical metrics engine | Sujal | DONE | HIGH | Analytics | 5 | 6 | math, numpy, statistics | 2026-10-10 11:30 | 2026-10-12 14:00
TASK-103 | Create multi-column ASCII terminal visualizer | Member3 | DONE | MEDIUM | CLI | 4 | 3.5 | terminal, ui, visualizer | 2026-10-11 09:00 | 2026-10-12 18:00
TASK-104 | Add state transition validation & constraint rules | Meet | REVIEW | CRITICAL | Core | 4.5 | 5 | core, state-machine, validation | 2026-10-12 10:00
TASK-105 | Implement bulk DataFrame boolean filtering engine | Sujal | IN_PROGRESS | HIGH | Backend | 5 | 4 | filtering, pandas, search | 2026-10-13 09:30
TASK-106 | Build automated Markdown & CSV report generator | Member3 | IN_PROGRESS | MEDIUM | Reporting | 3.5 | 2.5 | export, markdown, reports | 2026-10-13 11:00
TASK-107 | Support Excel (.xlsx) storage format via openpyxl | Meet | IN_PROGRESS | MEDIUM | Storage | 3 | 0 | excel, openpyxl, persistence | 2026-10-14 08:30
TASK-108 | Add outlier detection using 90th percentile threshold | Sujal | TODO | LOW | Analytics | 2.5 | 0 | math, numpy, outliers | 2026-10-14 09:00
TASK-109 | Write comprehensive unit tests for state machine | Member3 | TODO | HIGH | Testing | 4 | 0 | pytest, quality, testing | 2026-10-14 10:00
TASK-110 | Resolve third-party library dependency conflict | Meet | BLOCKED | CRITICAL | DevOps | 2 | 3 | blocking, bug, devops | 2026-10-14 10:30
TASK-111 | Hello world | Naman | IN_PROGRESS | MEDIUM | frontend | 1 | 2 | design, ui | 2026-10-14 20:46